## Slide 1
M | T | W | Th | F
3/9 | 3/10 | 3/11 Budget Deep Dive FFEWG Meeting COB: Send draft to Beth & Tony | 3/12 One-on-one DADs/BCs COB: Send draft to DADs & BCs | 3/13 OMB Pre-Clearance Review One-on-one DADs/BCs
3/16 PADs/DADs OMB Pre-Clearance Review | 3/17 (Incorp pre-clearance) COB: Enters OMB Clearance | 3/18 | 3/19 | 3/20
3/23 | 3/24 | 3/25 | 3/26 | 3/27
3/30 | 3/31 | 4/1 ----- START OF APRIL ---------- | 4/2 | 4/3
4/6 | 4/7 | 4/8 | 4/9 | 4/10
4/13 | 4/14 | 4/15 | 4/16 | 4/17
4/20 | 4/21 | 4/22 | 4/23 | 4/24
4/27 | 4/28 | 4/29 | 4/30 | 5/1 ----- START OF MAY----------
5/4 | 5/5 | 5/6 | 5/7 | 5/8
5/11 | 5/12 | 5/13 | 5/14 | 5/15
OMB Rounds 2
OMB Round 3
Agency LRM
Public Comments
Final OMB Clearance (1, 2, 3)
Final OMB Clearance (1, 2, 3)
Incorporate Comments / Slippage
Beth & Tony
Director
OMB Rounds 1
Beth & Tony
Beth & Tony
DADs Discussion?
Comms/GC/LA
Comms/GC/LA
Comms/GC/LA
Comms/GC/LA
Comms/GC/LA
DIR/Deputies/PAD (Tom?)
Public Comment
Hill Overview
Director and Deputies?
Beth & Tony
Beth & Tony
Beth & Tony
Meet with Hill on Details
RELEASE

## Slide 2: FITARA Outreach and Implementation
January 2015

## Slide 3: FITARA MAX Group
FYI, I requested a MAX group in case we want to use it for FITARA stuff. I mainly got it for MAX Shared Desktop in case we want to use it for meetings. We can also just always use the backup viewer which is Adobe Connect and the link for that would be: https://meetings.max.gov/agy-omb-egov_fitara/
Greetings:
I have created your Max group and granted you admin permissions. The details are below. Feel free to reach out to me or Max Support if you have any questions.
Group ID: AGY-OMB-EGOV.FITARA
Group Short Title: E-Gov FITARA
Group Title: OMB E-Gov FITARA Implementation Support
Group Shortcut URL: https://community.max.gov/x/GYQjLw
Group Member Types: Executive Branch

## Slide 4: FITARA Requirements
CIO Authorities
IT Dashboard
PortfolioStat
FDCCI Data Centers
IT Acquisition Cadres
FSSI Strategic Sourcing
Government-wide Software Purchasing Program
More resources, including the bill text:
https://community.max.gov/x/GYQjLw
For all feedback and questions, please contact Ben Sweezy at BSWEEZY@omb.eop.gov

## Slide 5: FITARA Sections and Highlights
1. CIO Authorities (Ben)
  Requires CIO role or approval in IT planning, budget, contract, reprogramming, governance, reporting, and hiring of bureau/component CIOs.
  Most of this does not apply to DOD or intelligence work, but DOD CIO does have to make recommendations to the SECDEF about the IT budget and certify that OMB guidance on incremental development is being adequately implemented at DOD.
2. IT Dashboard (Mishu)
  Puts the public availability of major IT investment cost, schedule, and performance data into law but gives OMB flexibility into how to do that (i.e. does not name “IT Dashboard” specifically).
  Requires automatic OMB TechStats on investments which “receive a high risk rating for four consecutive quarters”—which likely will mean a red CIO Evaluation. The word TechStat is not used but that is likely how we will interpret it—
    FITARA requires certain mechanics during these reviews. The results of the TechStat must be reported to Congress—probably through the ITOR Quarterly Report. DOD has the option to conduct this on their own without OMB.
  If an investment is still red one year following an OMB TechStat, FITARA requires OMB to deny any request for additional DME funding for the investment until the agency CIO determines that it is back on track
3. PortfolioStat (Mary)
  Requires annual reviews between OMB E-Gov, agency COO/DepSec, and agency CIOs of the IT portfolio at each agency. (The law does not use the word “PortfolioStat” but I will use it here for familiarity.)
    DOD’s review shall only apply to “business systems IT portfolio…and not to ‘national security systems’.” It will be carried out by DCMO in consultation with DOD CIO, USD/AT&L. SECDEF in consultation with OMB E-Gov can designate an existing DOD process to take the place of this annual review.
4. FDCCI Data Centers (Subu)
  Formalizes FDCCI in law.
  New reporting requirements
5. IT Acquisition Cadres (OFPP: Joanie N)
  OFPP consulting with E-Gov works with agencies to include IT acquisition human capital issues in “acquisition human capital plans.”
  Requires a series of topics to be addressed in those plans.
6. FSSI Strategic Sourcing (OFPP: Meredith)
  Within 180 days OFPP shall require that when agencies do not use FSSI for items covered under FSSI the contract file for the purchase shall include a brief analysis of the comparative value, including price and non-price factors, between the services and supplies offered under such Initiative and services and supplies offered under the source or sources used for the purchase.
7. Governmentwide Software Purchasing Program (OFPP: Meredith)
  Requires that software is included in strategic sourcing.
  Requires GSA to allow for the purchase of a license agreement that is available for use by all agencies as one user to the maximum extent practicable/appropriate.
Ben /
Tim M / Malissa
Mishu
Mary
Subu
OFPP
Joanie N
OFPP Meredith/
Mathew
OFPP Meredith

## Slide 6: Questions for OGC
Review comments on “FITARA Details for Agencies”
How to interact with GC community & how to select for FFEWG
FSGG General Provision CIO Authorities, brown bag
Leeway defining terms
Review exceptions
OMB Circular versus M-memo versus others

## Slide 7: FITARA Sections and Highlights
CIO Authorities (Ben)
IT Dashboard (Mishu)
PortfolioStat (Mary)
FDCCI Data Centers (Subu)
IT Acquisition Cadres (OFPP: Joanie N)
FSSI Strategic Sourcing (OFPP: Meredith)
Governmentwide Software Purchasing Program (OFPP: Meredith)

## Slide 8: FITARA CIO Authorities
Non-DOD CFO Act Agencies USDA Commerce ED Energy HHS DHS HUD Interior Justice Labor State DOT Treasury VA EPA NASA USAID GSA NSF NRC OPM SBA SSA | The following FITARA CIO authority statements apply: OMB guidance shall require that each CIO certify that IT investments are adequately implementing incremental development each CIO approve the IT budget request Post-FITARA, agencies… (These duties are not delegable unless otherwise specified) May not request the reprogramming of any funds made available for IT programs, unless the request has been reviewed and approved by the CIO of the agency; and May not enter into a contract or other agreement for IT or IT services, unless the contract or other agreement has been reviewed and approved by the CIO of the agency agencies may delegate this approval for non-major investments to an individual who reports directly to the CIO [However, agency] may use the governance processes of the agency to approve such a contract or other agreement if the CIO of the agency is included as a full participant in the governance processes. Other Authorities CIO shall approve the appointment of any other employee with the title of CIO, or who functions in the capacity of a CIO, for any component organization within the covered agency.” Head of each non-DOD agency shall ensure that the CIO of the agency has a significant role in— the decision processes for all annual and multi-year planning, programming, budgeting, and execution decisions, related reporting requirements, and reports related to IT; and the management, governance and oversight processes related to IT.
DOD | Of above, only the following apply to DOD: OMB CPIC guidance shall require that each agency CIO certify that IT investments are adequately implementing incremental development as defined in CPIC guidance DOD CIO review and provide recommendations to the SECDEF on the IT budget request.
Intelligence Community (Any IT or Telecom “fully funded” by NIP/MIP) | None of the above apply.

## Slide 9: Likely Policies Impacted
Implementation of E-Government Act (M-03-08)
CIO Authorities (M-11-29)
Yearly PortfolioStat Memos (M-12-13)
OMB Circular A-130 (CPIC, EA, IRM, etc)
A-11 IT Dashboard Guidance
Quarterly Agency Oversight / OMBStat

## Slide 10: Overall CONOPS
  Initial Outreach / Listening (January)
    Agencies identify FITARA Lead POC. POC then joins bi-weekly status calls.
  Drafting Approach/Memo (Jan/Feb)
  Stakeholder / Public Comment on Approach (March)
  Implementation (Post-April)

## Slide 11: Outreach Plan
Bi-weekly Status Phone Calls (Every other Wednesday starting mid-January)
Attendees: POC in charge of FITARA coordination for each agency, contacts in the CPIC, EA, CIOC, Cyber community.
Outreach Sessions (January)
CIO Council
CPIC Community (via CPIC Committee of CIOC and FESCOM)
Chief Architect’s Forum
ACT-IAC
SAGE via Partnership for Public Service
Hill
CAO Council
Comments
Collecting government stakeholder comments on MAX and email (closes 1/16)
Moving Forward
Establish staff level working group
Establish a multi-disciplinary working group
ISIMC (Cyber community)
Data Center Task Force
RMOs
PMC
GAO
BOAC
Higher Education
Agency GC Group

## Slide 12: Initial Outreach Complete
Outreach Sessions (January)
CIO Council
CPIC Community
Chief Architect’s Forum
ACT-IAC
SAGE via Partnership for Public Service
CAO Council
Comments
Collected 61 initial comments from agencies, plus 158 agency participants over 5 conference calls
CFO Council
CHCO Council
ISIMC (Cyber community)
Data Center Task Force
RMOs
ASAM Roundtable
PMC
BOAC
Higher Education
GC Roundtable
ISPAB
CIGIE
GAO

## Slide 13: OMB Alert Release January 30
From Beth Cobert (OMB DDM) to Deputy Secretaries and Assistant Secretaries for A/M
Subject: Forthcoming Gov-Wide Guidance on FITARA/FISMA
Also sent to CIO, CFO, CAO, CHCO, PMC Senior Advisors and GC distribution lists by OMB
Notified agencies that guidance:
  Will be released in “Spring 2015”
  Will address CIO role and key relationships
  Will define terms, giving examples
  Address governance processes and ethics or conflict of interest issues
Instructs agencies to take “reasonable steps to comply” in interim
Announced FFEWG

## Slide 14: FITARA Exec Working Group (FFEWG)
Selecting two reps from each community by working with each Council’s staff, agency chairpersons and the relevant OMB lead
Representatives should be: “senior executives with familiarity of current agency practices and culture around cross-management domain interactions and eager to think creatively about changes to how each management domain interfaces with CIOs, as well as think critically about the obstacles and difficulties involved with significant change.”
The communities to represent are:
  CIO
  CFO
  Budget officers
  CAO & Senior procurement executives
  CHCO
  General Counsel
  Assistant Secretary for Administration/Management (or equivalent)

## Slide 15
FITARA Outreach
FY 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  | 
Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FITARA Roadmap
Implementation
Clearance
(Red, LRM, 2nd)
Release
Draft Proposed Memo
Resources for Outreach | Sweezy
FITARA Bill Text | Sweezy
FITARA E-Gov Summary v2 | Sweezy
Old Memos: M-03-08, M-11-29, Pstat Memos, A-130, etc | Sweezy
Summary of new and old provisions | Sweezy
Standard Agenda for Stakeholder Meetings
We will be focusing on the following topics: FITARA Introduction and Context, OMB Outreach Plan Lessons from Implementation of the E-Government Act of 2002 CIO Authorities: Opportunities, Risks, and Obstacles Agencies & OMB Face Other FITARA Sections: Opportunities, Risks, and Obstacles
Meet with Beth
Meet with Beth
Meet with Beth
Stakeholder Outreach
Public Comment
Stakeholder Meetings | Contact Info | POC | Date | Status
CIO Council | Listserv | Malissa | Jan 14th (EC), joint CAOC/CIOC EC Jan 20; full Jan 28th | Complete
CPIC Committee of CIOC | Have emails | Malissa | Conference calls on Jan 21 at 11am, 22 at 10:30am , 23 at 10am and 2pm | Complete
Chief Architect’s Forum | Have emails | Malissa | Conference calls on Jan 21 at 11am, 22 at 10:30am , 23 at 10am and 2pm | Complete
ACT-IAC | Ken, Rick, Allen, Dan C | Sweezy | Jan 15 3:30pm | Complete
SAGE via Pship for Public Service | Austin Price | Sweezy | Jan 9, 4:30-5:30 | Complete
Hill | Jess Menter (OLA) | Sweezy | Late Jan. | 
CAO Council | Listserv | Sweezy | Joint CAO/CIO EC Jan. 20 1pm | Complete
USDS | Charles, Traci, Germaine | Sweezy | Hot topics Jan. 7 & 21 | Complete
ISIMC (Cyber community) | Have emails | Malissa w/ Alex/Trevor | Conference calls on Jan 21 at 11am, 22 at 10:30am , 23 at 10am and 2pm | Complete
E-Gov Staff in General | EGOV FED STAFF | Sweezy | Hot topics Jan. 7 & 21 | Complete
Data Center Task Force | Listserv | Malissa | Jan 15 at 1pm | Complete
FESCOM meeting | Dan York | Malissa & Mishu | Jan 21st at 9am | Complete
Beth Cobert |  | Sweezy | Jan 9, Feb 1 & 14 | 
RMO brownbag |  | Sweezy | Jan 12,& 13 12pm | Complete
PMC Chiefs of Staff (planning) | Julia | Jamie B | Jan 16 | 
Next PMC Meeting | Julia | Jamie B | Jan 24 | 
GAO | Dave Powner | Jamie | Jan 27 at 12pm | Complete
BOAC | TBD | Malissa | TBD | 
Higher Education | Joe Castle? | Sweezy | Call with Joe Jan 16 | Complete
Good government | Sunlight, effective gov, | Adam/Craig | TBD | 
Professional Associations |  | Sweezy | TBD | 
Agency OGC Group | Varun / Geovette | Sweezy | Contacted Varun. Date TBD | 
CFO Council | Mark Reger / Mary | Sweezy | Meeting with Mark Jan 20 | Complete
CIGIE during drafting | Kathy Tighe, Andy Patchin, Pete Sheridan | Sweezy | Meet #2 during mid-late Feb | 

## Slide 16
Stakeholder Meetings | Contact Info | POC | Date | Status
CIO Council | Listserv | Malissa | Jan 14th (EC), joint CAOC/CIOC EC Jan 20; full Jan 28; EC 2/11 | Complete
CPIC Committee of CIOC | Have emails | Malissa | Conference calls on Jan 21 at 11am, 22 at 10:30am , 23 at 10am and 2pm | Complete
Chief Architect’s Forum | Have emails | Malissa | Conference calls on Jan 21 at 11am, 22 at 10:30am , 23 at 10am and 2pm | Complete
ACT-IAC | Ken, Rick, Allen, Dan C | Sweezy | Jan 15 3:30pm | Complete
SAGE via Pship for Public Service | Austin Price | Sweezy | Jan 9, 4:30-5:30; weekly meetings starting 2/4 | Complete
Hill | Jess Menter (OLA) | Sweezy | OLA says revisit Hill outreach after week of 2/2 | OBE
CAO Council | Listserv | Sweezy | Joint CAO/CIO EC Jan. 20 1pm | Complete
USDS | Charles, Traci, Germaine | Sweezy | Hot topics Jan. 7 & 21 | Complete
ISIMC (Cyber community) | Have emails | Malissa w/ Alex/Trevor | Conference calls on Jan 21 at 11am, 22 at 10:30am , 23 at 10am and 2pm | Complete
E-Gov Staff in General | EGOV FED STAFF | Sweezy | Hot topics Jan. 7 & 21 | Complete
Data Center Task Force | Listserv | Malissa | Jan 15 at 1pm | Complete
FESCOM meeting | Dan York | Malissa & Mishu | Jan 21st at 9am | Complete
Beth Cobert |  | Sweezy | Jan 9, Feb 6 and Feb 19 | Complete or Scheduled
RMO brownbag (Jan) |  | Sweezy | Jan 12,& 13 12pm | Complete
RMO brownbags (Feb) |  | Malissa | Feb 25 & 26 | Scheduled
ASAM Roundtable |  | Sweezy | Feb 12 | Complete
ISPAB |  |  | Feb 13 | Complete
Stakeholder Meetings | Contact Info | POC | Date | Status
Frank Baitman 1-on-1 |  | Sweezy | Jan 12 | Complete
Stephen Warren 1-on-1 |  | Sweezy | Jan 28 | Complete
Kurt DelBene 1-on-1 |  | Sweezy | Jan 29 | Complete
PMC Chiefs of Staff | Julia | Jamie B | Jan 16 | Complete
January PMC Meeting | Julia | Jamie B | Jan 24 | Complete
GAO | Dave Powner | Jamie | Jan 27 at 12pm | Complete
BOAC | Shelly McAllister | Malissa | February/March | Scheduled
Higher Education | Joe Castle | Sweezy | Planning conf call week of Feb 9 | TBD
Good government | Sunlight, effective gov, | Adam/Craig | TBD | TBD
Professional Associations |  |  | Planning for March comment | TBD
GC Roundtable | Varun / Geovette | Sweezy | 2/12/15 | Complete
CFO Council | Mark Reger / Mary | Sweezy | Meeting with Mark Jan 20; Also invited to March meet | Complete and Scheduled
CIGIE during drafting | Kathy Tighe, Andy Patchin, Pete Sheridan | Sweezy | Meet #2 on Feb 12; possibly final call after draft guidance | Complete and TBD
CSIS (FISMA/FITARA) | Karen Evans | Sweezy | Next couple weeks | TBD
CHCOC | Justin Johnson | Malissa | 2/4 and 2/10 | Complete
EPA implementation call | Renee Wynn | Sweezy | 2/3 | Complete
CEB | Kris van Riper | Sweezy/Craig | 2/10 | Complete
Private sector CIOs via CEB | Kris van Riper | Sweezy | 2/24 | Scheduling
Initial Outreach Complete
Two Rounds of Agency Comments:
E-Gov Mailbox and MAX Comments
61 comments from agencies rep 47% of Fed IT Spend

## Slide 17: Agenda
  FITARA Introduction and Context, OMB Outreach Plan
  Suggestions from EGA Implementation
  CIO Authorities: Opportunities, Risks, and Obstacles Agencies & OMB Face
  Other FITARA Sections: Opportunities, Risks, and Obstacles

## Slide 18: Suggestions from EGA Implementation
    Connecting FITARA and FISMA Implementation
    Release early vision quickly even if incomplete
    PMC: “Quad Council”—Select leaders from CXO community to ensure awareness; work through thorny issues; make recommendations;
    OMB/CIOC Standards for Agency Implementation Plans, individual agencies draft their plans
    CIOC-organized agency working group at practitioner level
    One Page Summary of Implementation To Circulate Broadly
    Hill outreach: bring a mature plan and highlight conflicts between laws, existing policy

## Slide 19: “Role of the CIO” FITARA Guidance
Budget formulation (“IT budget”?)
Reprogramming of funds
Budget execution, FM, and invoice review (discovering “shadow IT”)
Acquisition strategy, vehicle, requirements review
Contract review and approval
Approval of bureau CIOs and “CIOs”
CPIC “control” & “evaluate”: risk ratings, major investment reviews, annual portfolio review
Use of incremental development
(Any other planning, budgeting, execution, reporting decisions)

## Slide 20: Other FITARA Requirements
  IT Dashboard and OMB TechStat
  PortfolioStat
  FDCCI Data Centers (Metrics and Reporting)
  Other Initiatives
    IT Acquisition Cadres
    FSSI Strategic Sourcing
    Government-wide Software Purchasing Program

## Slide 21
 | CIO | CFO | CAO | CBO
PLANNING |  |  |  | 
PROGRAMMING |  |  |  | 
BUDGETING |  |  |  | 
EXECUTION |  |  |  | 

## Slide 22: January – Detailed Timeline
M | T | W | Th | F
1/5 Intro call with SAGE | 1/6 | 1/7 E-gov hot topics | 1/8 - MAX comments open - Send targeted emails | 1/9 Former E-gov staff and administrators meeting on lessons learned SAGEs meeting
1/12 RMO brownbag | 1/13 RMO brownbag | 1/14 CIOC EC meeting | 1/15 Data Center TF meeting | 1/16 MAX comments close
1/19 | 1/20 CIOC/CAOC EC meeting | 1/21 | 1/22 | 1/23
1/26 | 1/27 GAO meeting | 1/28 Full CIOC meeting | 1/29 | 1/30
Initial stakeholder meetings
Review and analyze comments
Hold additional conference calls
Summarize and come up with conclusions
Bi-Weekly Status Call
Bi-Weekly Status Call

## Slide 23: February – Detailed Timeline
M | T | W | Th | F
2/2 | 2/3 A-130 FITARA Check-In | 2/4 SAGE Meeting BOAC Staff | 2/5 | 2/6 A-130 revisions due DDM meeting PMC Meeting
2/9 | 2/10 OMB M4+2 Meeting CHCOC Meeting | 2/11 SAGE Meeting CIO Council Meeting | 2/12 | 2/13 (DDM meeting?) Comms/Leg meeting
2/16 | 2/17 | 2/18 FFEWG Meeting SAGE Meeting | 2/19 OMB M4+2 Meeting SSLC Meeting | 2/20
2/23 | 2/24 CIO FITARA Meeting CEB private sector CIOs meeting | 2/25 FFEWG Meeting SAGE Meeting CIO Council Meeting (Cyber) | 2/26 OMB M4+2 Meeting RMO Brownbag | 2/27 Goes into clearance
Review and analyze comments
Present High-Level Decisions to Beth/DDM
Final Additional Decisions by Beth/DDM
Present High-Level Decisions to Beth/DDM
Notes: Drafting guidance will draw on the following groups:
FITARA Section Leaders (E-Gov and OFPP) draft “Section Templates” by Feb 4
A-130 Revisions due February 6
FFEWG meets weekly starting Feb 11
SAGE (PPS) group meets weekly starting Feb 4
Internal OMB “M4+2” group of FITARA leads: plus BOAC/BRD & OGC weekly
Last steps outreach to CIOC, FFEWG to PMC
Enters clearance at end of February

## Slide 24
M | T | W | Th | F
3/2 | 3/3 | 3/4 Budget Deep Dive FFEWG Meeting COB: Send draft to DADs & BCs | 3/5 OMB Pre-Clearance Review | 3/6 OMB Pre-Clearance Review
3/9 | 3/10 | 3/11 | 3/12 | 3/13
3/16 | 3/17 | 3/18 | 3/19 | 3/20
3/23 | 3/24 | 3/25 | 3/26 | 3/27
3/30 | 3/31 | 4/1 ----- START OF APRIL ---------- | 4/2 | 4/3
4/6 | 4/7 | 4/8 | 4/9 | 4/10
4/13 | 4/14 | 4/15 | 4/16 | 4/17
4/20 | 4/21 | 4/22 | 4/23 | 4/24
OMB Rounds 1, 2, 3
OMB Rounds 1, 2, 3
Agency LRM
Public Comments
Agency LRM
Public Comment
Final OMB Clearance (1, 2, 3)
Final OMB Clearance (1, 2, 3)
Incorporate Comments / Slippage
Incorporate Agency Comments
Beth & Tony
Beth & Tony
Beth & Tony
Director and Deputies?
Director and Deputies?

## Slide 25
Present High-Level Decisions to Beth/DDM
Final Additional Decisions by Beth/DDM
Present High-Level Decisions to Beth/DDM
M | T | W | Th | F
3/2 | 3/3 | 3/4 COB: Send draft to DADs & BCs | 3/5 OMB Pre-Clearance Review | 3/6 OMB Pre-Clearance Review
3/9 | 3/10 | 3/11 | 3/12 | 3/13
3/16 | 3/17 | 3/18 | 3/19 | 3/20
3/23 | 3/24 | 3/25 | 3/26 | 3/27
3/30 | 3/31 | 4/1 | 4/2 | 4/3
4/6 |  |  |  | 
4/13 |  |  |  | 
4/20 |  |  |  | 
OMB Rounds 1, 2, 3
OMB Rounds 1, 2, 3
Agency LRM
Public Comments
Agency LRM
Public Comment
Final OMB Clearance (1, 2, 3)
Final OMB Clearance (1, 2, 3)
Incorporate Comments / Slippage
Incorporate Agency Comments

## Slide 26: General E-Gov FY15 Policy Outlook
FY 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  | 
Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | 
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
FITARA Roadmap
Implementation
Release
Meet with Beth
Stakeholder Outreach
FISMA
2014
Hill Outreach
OMB Circular A-130
Implementation
Release
Stakeholder Outreach
Cybersecurity Breach Memo Updates
Release
Stakeholder Outreach
Public Comment
1st Draft
FINAL
Drafting
Incorporate
Public Comment
Cyber BDR
Incident Guidance
FISMA Report
Update ISCM
CONOPS
Recovery Guidance
Patch Guidance
Cyber BDR
Initial Notifi-cation

## Slide 27: Appendix
  Detailed FITARA Requirements (5 slides)
  Core OMB FITARA Contact List

## Slide 28: FITARA Sections (page 1 of 4)
Non-DOD CFO Act Agencies USDA Commerce ED Energy HHS DHS HUD Interior Justice Labor State DOT Treasury VA EPA NASA USAID GSA NSF NRC OPM SBA SSA | The following FITARA CIO authority statements apply: OMB CPIC guidance shall require that each CIO certify that IT investments are adequately implementing incremental development each CIO approve the IT budget request CIO Duties (These duties are not delegable unless otherwise specified) May not request the reprogramming of any funds made available for IT programs, unless the request has been reviewed and approved by the CIO of the agency; and May not enter into a contract or other agreement for IT or IT services, unless the contract or other agreement has been reviewed and approved by the CIO of the agency agencies may delegate this approval for non-major investments to an individual who reports directly to the CIO [However, agency] may use the governance processes of the agency to approve such a contract or other agreement if the CIO of the agency is included as a full participant in the governance processes. Other Authorities CIO shall approve the appointment of any other employee with the title of CIO, or who functions in the capacity of a CIO, for any component organization within the covered agency.” Head of each non-DOD agency shall ensure that the CIO of the agency has a significant role in— the decision processes for all annual and multi-year planning, programming, budgeting, and execution decisions, related reporting requirements, and reports related to IT; and the management, governance and oversight processes related to IT.
DOD | Of above, only the following apply to DOD: OMB CPIC guidance shall require that each agency CIO certify that IT investments are adequately implementing incremental development as defined in CPIC guidance DOD CIO review and provide recommendations to the SECDEF on the IT budget request.
Intelligence Community (Any IT or Telecom “fully funded” by NIP/MIP) | None of the above apply.

## Slide 29: FITARA Sections (page 2 of 4)
832. IT Dashboard
  Puts the public availability of major IT investment cost, schedule, and performance data into law but gives OMB flexibility into how to do that (i.e. does not name “IT Dashboard” specifically).
  Requires automatic OMB TechStats on investments which “receive a high risk rating for four consecutive quarters”—which likely will mean a red CIO Evaluation. The word TechStat is not used but that is likely how we will interpret it—
    FITARA requires certain mechanics during these reviews. The results of the TechStat must be reported to Congress—probably through the ITOR Quarterly Report. DOD has the option to conduct this on their own without OMB.
  If an investment is still red one year following an OMB TechStat, FITARA requires OMB to deny any request for additional DME funding for the investment until the agency CIO determines that it is back on track to deliver “remaining planned increments within the planned cost and schedule.” Still thinking through the implications of this, but we know of two investments that would meet this criteria today: Education ED Web and DHS ICE-TECS Modernization.
  Requires OMB guidance to strengthen agency CIO evaluations and data reporting in general—we’re still working through the specifics.
  Note: final legislation dropped requirement that IT Dashboard be continuously publicly available all year round.
  Intelligence programs and “National security interests” as determined by OMB Director and are excepted from IT Dashboard requirements. Still working through the specifics of what this means for DOD/ODNI investment reporting but this is probably no change from previous practice.
833. PortfolioStat
  Requires annual reviews between OMB E-Gov, agency COO/DepSec, and agency CIOs of the IT portfolio at each agency. (The law does not use the word “PortfolioStat” but I will use it here for familiarity.)
    DOD’s review shall only apply to “business systems IT portfolio…and not to ‘national security systems’.” It will be carried out by DCMO in consultation with DOD CIO, USD/AT&L. SECDEF in consultation with OMB E-Gov can designate an existing DOD process to take the place of this annual review.
  Beyond those reviews, requires that OMB “implement a process to assist…agencies in reviewing their portfolio of IT investments” and specifies a series of goals and topics such assistance must cover and the establishment of metrics, largely in line with previous PortfolioStat strategies.
  Brings back specific multi-year cost savings plans as a part of PortfolioStat, similar to the commodity IT plans required in 2012 PortfolioStat sessions.
  The cost savings portion of the Quarterly ITOR Report related to “duplicative IT investments” must be sent to HSGAC, HOGR and any other committee that requests it in addition to its current recipients (Approps and GAO).

## Slide 30: FITARA Sections (page 3 of 4)
834. FDCCI Data Centers
  Formalizes FDCCI in law.
  New reporting requirements
    Annual inventory. Each agency must submit data center inventory of data centers “owned, operated, or maintained by or on behalf of the agency”—still evaluating whether this is an expansion in scope of existing FDCCI inventory requirements.
    Annual strategy. Multi year strategy to achieve consolidation and optimization, including
      performance metrics
      timeline for agency FDCCI activities, including benchmarks to achieve by specific dates
      year-by-year calculations of investment and cost savings going forward
      E-Gov is still evaluating whether this “multi-year strategy” can continue to be integrated within agency inventories and existing cost/savings reporting rather than as stand alone documents.
    Annual statement. Agencies must submit to OMB and post publicly an annual statement describing compliance with these requirements. Still exploring whether this could be included in existing reporting requirements such as IRM strategic plan.
    Quarterly updates. Additionally, agencies must provide quarterly updates to OMB on FDCCI progress, metrics progress, and cost savings. Likely to include this in existing FDCCI or IDC reporting.
    DOD exceptions. DOD is given the option of alternative inventory and reporting mechanisms under other NDAA performance plans for reduction of resources. DOD also is given an alternative to the multi-year strategy based on other parts of NDAA.
    OMB Public Goal and Annual Reporting
      OMB E-Gov must publish publicly within a year a “goal” for cost savings and optimization targets by year going forward and submit the goal to Congress
      OMB E-Gov must publish publicly annually FDCCI savings and optimization progress for each agency each year going forward and compare actual progress to agency strategies
      OMB E-Gov must report to Congress annually a statement comprehensiveness of each agency inventory and an analysis of the inventories, and comprehensiveness of each agency strategy.
      OMB E-Gov must make govwide progress available to the public “in a timely manner”
    GAO annual report and review. To verify inventory and strategies at each agency.
  OMB E-Gov must establish reporting deadlines, requirements, review inventories and strategies, monitor implementation of strategies, annually update FDCCI cumulative cost savings, establish cost and efficiency metrics.
  FDCCI must be consistent with FedRAMP and NIST guidance on cloud computing security.

## Slide 31: FITARA Sections (page 4 of 4)
835. IT Acquisition Cadres
  OFPP consulting with E-Gov works with agencies to include IT acquisition human capital issues in “acquisition human capital plans.”
  Requires a series of topics to be addressed in those plans.
836. FSSI Strategic Sourcing
  Within 180 days OFPP shall require that when agencies do not use FSSI for items covered under FSSI the contract file for the purchase shall include a brief analysis of the comparative value, including price and non-price factors, between the services and supplies offered under such Initiative and services and supplies offered under the source or sources used for the purchase.
837. Governmentwide Software Purchasing Program
  Requires that software is included in strategic sourcing.
  Requires GSA to allow for the purchase of a license agreement that is available for use by all agencies as one user to the maximum extent practicable/appropriate.

## Slide 32: Core OMB FITARA Contact List
E-Gov and USDS
Sweezy, Benjamin R. <Benjamin_R._Sweezy@omb.eop.gov>;
Berryhill, Jamie <Jamie_L_Berryhill@omb.eop.gov>;
McCrosson, Tim <Timothy_D_McCrosson@omb.eop.gov>;
Bales, Carol A. <Carol_A._Bales@omb.eop.gov>;
Lazzeri, Mary <Mary_A_Lazzeri2@omb.eop.gov>;
Rahman, Mishu <Moshiur_Rahman@omb.eop.gov>;
Levesque, Malissa <Malissa_Levesque@omb.eop.gov>;
Gabriel, Germaine <Germaine_G_Gabriel@omb.eop.gov>;
Walker, Traci L. <Traci_L_Walker@omb.eop.gov>;
Worthington, Charles <Charles_E_Worthington@omb.eop.gov>;
Mirza, Asma Asma_Y._Mirza@omb.eop.gov
Dickerson, Mikey Mikey_A_Dickerson@omb.eop.gov
Van Dyck, Haley Haley_L_VanDyck@omb.eop.gov
Langley, Alexandra <Alexandra_K_Langley@omb.eop.gov>
OFPP colleagues:
Newhart, Joanie <Joan_F._Newhart@omb.eop.gov>;
Blum, Mathew C. <Mathew_C._Blum@omb.eop.gov>;
Romley, Meredith B. <Meredith_B._Romley@omb.eop.gov>;
Other OMB stakeholders as relevant:
Tom Hitter and Varun Jain (OGC)
Jeremy (OPPM for HR topics)
Jess Menter and Allie Neill (OLA)
Jamal Brown (Comms)
Regina Kearney (OFFM)
Nick Fraser (OIRA)
Rowe, David <David_Rowe@omb.eop.gov>
FITARA RMOs
Kearney, Regina L. <Regina_L._Kearney@omb.eop.gov>; Hurban, James C. <James_C._Hurban@omb.eop.gov>; Allred, Victoria L. <Victoria_L._Allred@omb.eop.gov>; Skidmore, Ben <Benjamin_J_Skidmore@omb.eop.gov>; Banjade, Pratik <Pratik_S_Banjade@omb.eop.gov>; Reczek, Jeff <Jeffrey_Reczek@omb.eop.gov>; Hatchett, Alyson <Alyson_M_Hatchett@omb.eop.gov>
Notes: Sweezy, Benjamin R. <Benjamin_R._Sweezy@omb.eop.gov>; Berryhill, Jamie <Jamie_L_Berryhill@omb.eop.gov>; McCrosson, Tim <Timothy_D_McCrosson@omb.eop.gov>; Lazzeri, Mary <Mary_A_Lazzeri2@omb.eop.gov>; Rahman, Mishu <Moshiur_Rahman@omb.eop.gov>; Levesque, Malissa <Malissa_Levesque@omb.eop.gov>; Gabriel, Germaine <Germaine_G_Gabriel@omb.eop.gov>; Walker, Traci L. <Traci_L_Walker@omb.eop.gov>; Worthington, Charles <Charles_E_Worthington@omb.eop.gov>; Newhart, Joanie <Joan_F._Newhart@omb.eop.gov>; Blum, Mathew C. <Mathew_C._Blum@omb.eop.gov>; Romley, Meredith B. <Meredith_B._Romley@omb.eop.gov>; Hitter, Thomas E. <Thomas_E._Hitter@omb.eop.gov>; Jain, Varun <Varun_M_Jain@omb.eop.gov>; Leon, Jeremy <Jeremy_L._Leon@omb.eop.gov>; Menter, Jessica <Jessica_N._Menter@omb.eop.gov>; Neill, Allie <Allie_R_Neill@omb.eop.gov>; Brown, Jamal <Jamal_T_Brown@omb.eop.gov>; Reger, Mark <Mark_A_Reger@omb.eop.gov>; Fraser, Nicholas A. <Nicholas_A._Fraser@omb.eop.gov>; Kearney, Regina L. <Regina_L._Kearney@omb.eop.gov>; Banjade, Pratik <Pratik_S_Banjade@omb.eop.gov>; Reczek, Jeff <Jeffrey_Reczek@omb.eop.gov>; Rowe, David <David_Rowe@omb.eop.gov>; Langley, Alexandra <Alexandra_K_Langley@omb.eop.gov>

## Slide 33: Agenda for Stakeholder Meetings
All,
We’re looking forward to our discussion at 4:30 pm tomorrow. Our preference is for folks to attend in person at:
New Executive Office Building, Room 7215
725 17th ST NW
Washington, DC
To attend in person, please contact Denise Jones to complete the building access requirements (Denise_M._Bray@omb.eop.gov). If you must call in, please use: 202-395-6392 code 9906740#.
We will be focusing on the following topics:
  FITARA Introduction and Context, OMB Outreach Plan
  Lessons from Implementation of the E-Government Act of 2002
  CIO Authorities: Opportunities, Risks, and Obstacles Agencies & OMB Face
  Other FITARA Sections: Opportunities, Risks, and Obstacles
Our summary of the sections of FITARA is:
  CIO Authorities
  IT Dashboard
  PortfolioStat
  FDCCI Data Centers
  IT Acquisition Cadres
  FSSI Strategic Sourcing
  Governmentwide Software Purchasing Program
Ben Sweezy
Strategy Lead, OMB E-Government and IT

## Slide 34: FITARA SOAs
Agency | POC Name | POC Title | POC Email
Commerce | Ellen Herbst | CFO/ASA | EHerbst@doc.gov
DHS | Chip Fulghum; Vince Micone | Chief Financial Officer; Chief of Staff for Management Directorate | chip.fulghum@hq.dhs.gov; vincent.micone@hq.dhs.gov
DOD | Terry Halvorsen | CIO | terry.a.halvorsen2.civ@mail.mil
Education | Andrew Jackson | Assistant Secretary for Management | andrew.jackson@ed.gov
Energy | David M. Klaus | Deputy Under Secretary for Management and Performance | David.Klaus@Hq.Doe.Gov
EPA | A. Stan Meiburg | Acting Deputy Administrator | Meiburg.Stan@epa.gov
HHS | Ned Holland | Assistant Secretary for Administration | Ned.Holland@hhs.gov
Justice | Rick Chandler | Director, Policy & Planning, Office of CIO | Richard.Chandler@usdoj.gov
Labor | T. Michael Kerr | Assistant Secretary for Administration and Management | Kerr.Michael@dol.gov
NASA | Krista Paquin | ‎Deputy Associate Administrator for Mission Support at NASA | krista.c.paquin@nasa.gov
OPM | Angela Bailey | Chief Operating Officer | Angela.Bailey@opm.gov
SSA | Bill Zielinski | CIO/Deputy Commissioner for Systems | Bill.Zielinski@ssa.gov
State | Patrick Kennedy (Overall Lead), Patrcia Lacina (Functional Lead) | Under Secretary of State for Management (Kennedy), Deputy CIO for Business Management and Planning (Lacina) | KennedyPF@state.gov; LacinaPA@state.gov
Treasury | Brodi Fontenot | Assistant Secretary for Administration | Brodi.Fontenot@treasury.gov
USAID | Angelique Crumbly | Head of Management Bureau with CIO Oversight | acrumbly@usaid.gov
VA | Stephen Warren | VA CIO | Stephen.Warren@va.gov

## Slide 35: POCs (all remaining slides)
Stakeholder | Contact Information
CPIC Committee of CIOC | See details
EA Community | See details
ACT-IAC | Dan Chenok
SAGE via Partnership for the Public Service | Austin and Tina: APrice@ourpublicservice.org; tsung@ourpublicservice.org
CAO Council Staff | Staff POC; full listserv: CAO-COUNCIL@LISTSERV.GSA.GOV
Cyber something? ISIMC | 
E-Gov staff | DL-OMB-EGOV; dl-omb-egov@dsr.eop.gov
Data Center Task Force | Chair: Joe Klimavicz; joseph.klimavicz@usdoj.gov Members: CIOC-FDCCI@LISTSERV.GSA.GOV
FESCOM | 
CIOC whole list | Go through Adam and Craig
CIOC EC | Go through Adam and Craig

## Slide 36: CPIC Contact Information
steve.thayer@usdoj.gov; Beth.Ward@faa.gov; Stephen.Schultz@opm.gov; Rebecca.Nichols@HQ.DHS.GOV; sSimon@doc.gov; Lisa.Alsop@hhs.gov; kelly_morrison@ios.doi.gov; Francis.O'Hearn@treasury.gov; carla.tucker@ed.gov; Vickie.Smith@nrc.gov; lori.parker-1@nasa.gov; Clark.Kevin.G@dol.gov
IDC Invitee List: lisa.alsop@hhs.gov'; 'janice.l.ausby@hud.gov'; 'abarrett-blake@usaid.gov'; 'carol.blackston@hq.doe.gov'; 'harold.b.blunt@usace.army.mil'; 'Sean.A.Bowie@hud.gov'; 'sboyd@nsf.gov'; 'lesley.briante@gsa.gov'; 'sylvia_burns@ios.doi.gov'; 'christopher.carlin@nara.gov'; 'ron.carter@ssa.gov'; 'john.casteel@osd.mil'; 'clark.kevin.g@dol.gov'; 'angela.cobb@usdoj.gov'; 'tyrone.crawley@ssa.gov'; 'Stephen.Czajka@ssa.gov'; 'tyrrell.eccles@va.gov'; 'ergenbrightde@state.gov'; 'tereda.j.frazier@nasa.gov'; 'freeman.fawn@epa.gov'; 'joseph.gee@opm.gov'; 'william.gehrke@hhs.gov'; 'antoinetta.grant@ocio.usda.gov'; 'carey.grunwald@va.gov'; 'michael.harris@gsa.gov'; 'patrice.haynesworth@sba.gov'; 'tanya.hicks@ocio.usda.gov'; 'daniel.hrouda@treasury.gov'; 'hunt.james@epa.gov'; 'otto.immink@ssa.gov'; 'tracey.jackson@dot.gov'; 'yvonne.jackson@ocio.usda.gov'; 'jones.beth@epa.gov'; 'nkaplan@nsf.gov'; 'robert.v.kazimer@usace.army.mil'; 'michael.kernich@gsa.gov'; 'leah.kube@nrc.gov'; 'kumarraj.sabina@epa.gov'; 'paula.r.law@usace.army.mil'; 'ann.liberatore@gsa.gov'; 'andrew.lu@ed.gov'; 'sally.mahoney@us.army.mil'; 'peggy.martin@hq.dhs.gov'; 'martinsx@state.gov'; 'rom.mascetti@va.gov'; 'franklyn.matthews@sba.gov'; 'walter.mcdonald@dot.gov'; 'marilyn.mitchell@ed.gov'; 'ken.moore@ed.gov'; 'Kelly_C_Morrison@ios.doi.gov'; 'rebecca.nichols@dhs.gov'; 'francis.o'hearn@treasury.gov'; 'gregory_obaugh@ios.doi.gov'; 'lori.parker-1@nasa.gov'; 'patrick.plunkett@gsa.gov'; 'dorothy.powell-moore@sba.gov'; 'houman.rasouli@nrc.gov'; 'rrees@nsf.gov'; 'jeanine.rites@ssa.gov'; 'helena.robinson@faa.gov'; 'faith.roy@va.gov'; 'kevin_schmitt@ios.doi.gov'; 'stephen.schultz@opm.gov'; 'mike.seckar@gsa.gov'; 'SSIMON@DOC.GOV'; 'aesmith@nsf.gov'; 'jacob.tepp@dot.gov'; 'steve.thayer@usdoj.gov'; 'carla.tucker@ed.gov'; 'dornesia.ward@usace.army.mil'; 'beth.ward@faa.gov'; 'timothy.weigel@va.gov'; 'erin.weston@dot.gov'; 'daniel.wilhelmi@ssa.gov'; 'eric.won@sba.gov'; 'burbad@si.edu'; 'cattaneov@si.edu'; 'nicklas.ron@pbgc.gov'; 'andrea.adams@hq.doe.gov'; 'flip.anderson@ocio.usda.gov'; 'vernelle.archer@ocio.usda.gov'; 'shilpa.arora@nrc.gov'; 'megan.baburek@do.treas.gov'; 'bailey.gladys@dol.gov'; 'karen.baker@usdoj.gov'; 'claire.barrett@dot.gov'; 'sarah_bassett@ios.doi.gov'; 'behm.robert@dol.gov'; 'bowie.sean.a@dol.gov'; 'christopher.brause@ed.gov'; 'Breitenother, Lauren' <Lauren.Breitenother@dot.gov>; 'james.c.brown2@usace.army.mil'; 'metrica.charleen.brown@census.gov'; 'stanley.a.buch@hud.gov'; 'campbell.carl.v@dol.gov'; 'oscar.carranza@hhs.gov'; 'thomas.chung@nist.gov'; 'brenda.coblentz@hq.doe.gov'; 'steven.corey-bey@ed.gov'; 'george.costantino@uspto.gov'; 'crawford.tim@epa.gov'; 'christophe.demontille@hhs.gov'; 'balint.decheke@hq.doe.gov'; 'jawayne.davis@bis.doc.gov'; 'luis_enriquez@ios.doi.gov'; 'gary.evans@osd.mil'; 'jose.r.finn.civ@mail.mil'; 'susan.gabriel-smith@ocio.usda.gov'; 'kurt.garbars@gsa.gov'; 'kevin.garrison@osd.mil'; 'heather.m.garritty@usdoj.gov'; 'Jean.Gilleo@usace.army.mil'; 'joe.gomes@nasa.gov'; 'vanessa.m.harden@census.gov'; 'jharper@doc.gov'; 'jonah.hatfield@gsa.gov'; 'stephen.heaps@nara.gov'; 'niles.hewlett@dot.gov'; 'frank.hoeppel@wdc.usda.gov'; 'dhoughton@ntis.gov'; 'hughes.xavier@dol.gov'; 'kenyatta.jackson@nrc.gov'; 'todd.johnson@ocio.usda.gov'; 'jonescy1@state.gov'; 'jones-parra.lisa@epa.gov'; 'deborah.a.kennedy@usace.army.mil'; 'kkerttula@usaid.gov'; 'rklemmer@ntia.doc.gov'; 'pkristobek@usaid.gov'; 'rick.lauderdale@hq.doe.gov'; 'LayRG@state.gov'; 'leaf.dawn.m@dol.gov'; 'robert.lee@hq.doe.gov'; 'meneshea.d.levy@usdoj.gov'; 'edison.lewark@uspto.gov'; 'lashayla.logan@hq.doe.gov'; 'matthew.long@dot.gov'; 'christopher.lowe@ocio.usda.gov'; 'Rich.Lowe@USPTO.Gov'; 'priscia.macgregor@hq.doe.gov'; 'jmahanand@usaid.gov'; 'Manning.Tonya@dol.gov'; 'mmaraya@doc.gov'; 'paul.mayhew@hhs.gov'; 'walter.mcdonald@dot.gov'; 'william.mckelvy@gsa.gov'; 'lisa.mendis@usdoj.gov'; 'Michelle.Miles@hq.doe.gov'; 'thomas.milligan@do.treas.gov'; 'dan.morgan.ctr@dot.gov'; 'dennis.morgan@noaa.gov'; 'rodolph.r.morrison.civ@mail.mil'; 'richard_mortell@ios.doi.gov'; 'mulcahy.sandra@dol.gov'; 'patrick.mulcare@gsa.gov'; 'carrie.neumayer.ctr@dot.gov'; 'hung.nguyen@nara.gov'; 'asghar.noor@sba.gov'; 'joseph.norton@gsa.gov'; 'mark.odonnell@ssa.gov'; 'okorovn@state.gov'; 'kopoku@usaid.gov'; 'andrew.orndorff@dot.gov'; 'ouyachi.hamid@dol.gov'; 'karen.overall@gsa.gov'; 'lawrence.b.packard@usdoj.gov'; 'mary.palmer@bea.gov'; 'penny.pastiva@hq.dhs.gov'; 'brian.peltier@ssa.gov'; 'pulsifer.michael@dol.gov'; 'michael.pupjakjr@hq.doe.gov'; 'ramirez.adrienne@dol.gov'; 'Deborah.Rauser@ssa.gov'; 'joshua_rhodes@ios.doi.gov'; 'ritchie.duyen.t@dol.gov'; 'asalah@oig.doc.gov'; 'lisa.a.schmitt@usdoj.gov'; 'kristine.seen@ocio.usda.gov'; 'seganish.roger@dol.gov'; 'gary.m.seibert@usace.army.mil'; 'paul.sforza@do.treas.gov'; 'yen.shan@sba.gov'; 'robert.sile@ocio.usda.gov'; 'ssingh@usaid.gov'; 'ksingletary@ntis.gov'; 'larry.slaughter@dot.gov'; 'rod.smart@trade.gov'; 'smialowicz.thomas@dol.gov'; 'arthur.smith@nrc.gov'; 'soni.param@epa.gov'; 'joshua.spicka@nrc.gov'; 'sullivan.peter@dol.gov'; 'gtara@eda.gov'; 'steve.thayer@usdoj.gov'; 'carl.triplett@dot.gov'; 'john.j.tyszka@census.gov'; 'adam.l.understein.ctr@mail.mil'; 'carlos.j.vargas@hud.gov'; 'david.waddell@ocio.usda.gov'; 'heidi.a.walton@census.gov'; 'michael.wash@nara.gov'; 'dianne.b.watkins.ctr@mail.mil'; 'michael.wayson@osd.mil'; 'whiteside.fred.e@dol.gov'; 'darryl.wilcox@sba.gov'; 'kimberly.m.williams@usdoj.gov'; 'stuart.williams@ed.gov'; 'kevin.wince@gsa.gov'; 'travis.winn@opm.gov'; 'david.young.ctr@dot.gov'; 'Gantt, Rhonda -OCIO' <Rhonda.Gantt@ocio.usda.gov>; 'Gumbs, Naomi - OCIO' <Naomi.Gumbs@ocio.usda.gov>; 'Boudreaux, Kimberly - OASAM' <Boudreaux.Kimberly@dol.gov>; 'Shine Kevin' <Shine.Kevin@pbgc.gov>; 'Vo Hiep' <Vo.Hiep@pbgc.gov>; 'Christopher Carlin' <christopher.carlin@nara.gov>; 'Thomas Smialowicz' <smialowicz.thomas@dol.gov>; 'Ann Smith' <aesmith@nsf.gov>; 'Vanessa Okoro' <okorovn@state.gov>; 'Penelope Pastiva' <penny.pastiva@hq.dhs.gov>; 'Duyen Ritchie' <ritchie.duyen.t@dol.gov>; 'Naomi Gumbs' <naomi.gumbs@ocio.usda.gov>; 'Antoinetta Grant' <antoinetta.grant@ocio.usda.gov>; 'Stuart Williams' <stuart.williams@ed.gov>; 'Steven Thayer' <steve.thayer@usdoj.gov>; 'Nhien Be' <nhien.be@treasury.gov>; 'Meneshea Levy' <meneshea.d.levy@usdoj.gov>; 'Thomas Milligan' <thomas.milligan@do.treas.gov>; 'Micki Miles' <michelle.miles@hq.doe.gov>; 'Kenneth Kerttula' <kkerttula@usaid.gov>; 'Kimberly Boudreaux' <boudreaux.kimberly@dol.gov>; 'Mary Palmer' <mary.palmer@bea.gov>; 'Kwadwo Opoku' <kopoku@usaid.gov>; 'Jose Finn' <jose.r.finn.civ@mail.mil>; 'Sarah Bassett' <sarah_bassett@ios.doi.gov>; 'Bradley Tubesing' <tubesing.bradley.d@dol.gov>; 'Roger Seganish' <seganish.roger@dol.gov>; 'Travis Winn' <travis.winn@opm.gov>; 'Delphine Dennis' <delphine.dennis@ocio.usda.gov>; 'Rebecca Nichols' <rebecca.nichols@dhs.gov>; 'Carol Blackston' <carol.blackston@hq.doe.gov>; 'Otto Immink' <otto.immink@ssa.gov>; 'Kimberly Hennings' <kimberly.hennings@ocio.usda.gov>; 'Rhonda Gantt' <rhonda.gantt@ocio.usda.gov>; 'Jonah Hatfield' <jonah.hatfield@gsa.gov>; 'Paul Mayhew' <paul.mayhew@hhs.gov>; 'Carlos Vargas' <carlos.j.vargas@hud.gov>; 'Jawayne Davis' <jawayne.davis@bis.doc.gov>; 'Adam Understein' <adam.l.understein.ctr@mail.mil>; 'Arthur Smith' <arthur.smith@nrc.gov>; 'Tauqeer Aslam' <taslam@blm.gov>; 'Paul Doyle' <doyle.paul@epa.gov>; 'Tracey Jackson' <tracey.jackson@dot.gov>; 'Rory Brown' <brown.rory@dol.gov>; 'Martha Przysucha' <martha.m.przysucha@nasa.gov>; 'David Parrish' <parrish.david@epa.gov>; 'Kenyatta Jackson' <kenyatta.jackson@nrc.gov>; WCouch@doc.gov; Hoan.N.Nguyen@usdoj.gov; Payton.Akin@usdoj.gov; tran-lamM@state.gov; Kerr.Michael@dol.gov; Cheryl.powell@cms.hhs.gov; Michele.bailey@cms.hhs.gov; Samuel.P.Liles@usace.army.mil Charles.Santangelo@HQ.DHS.GOV Bodas.Shailesh@epa.gov

## Slide 37: Enterprise Architecture Contact Information
EdwarJF@ucia.gov
tpennington@doc.gov
steven.corey-bey@ed.gov
Rick.Lauderdale@hq.doe.gov
chris.chilbert@hq.dhs.gov
kevin.a.king@hud.gov
james.walterman@usdoj.gov
Larry.Slaughter@dot.gov
soni.param@epa.gov
Haseen.Uddin@nara.gov
Willard.peters-1@nasa.gov
esivagna@nsf.gov
Arthur.Smith@nrc.gov
JACKNL2@dni.gov
Adrian.Linz@opm.gov
Asghar.noor@sba.gov
sjarrett@usaid.gov
lloyd.thrower@va.gov
Hung.Nguyen@nara.gov
lesley.briante@gsa.gov
gail.kalbfleisch@hhs.gov
deborah.rauser@ssa.gov
Paul.Sforza@treasury.gov
David.Curtis@treasury.gov
Steven.Verber@hhs.gov
kevin.wince@gsa.gov
pastrau@nsa.gov
boudreaux.kimberly@dol.gov
robert.sile@usda.gov
Stephen.moore@treasury.gov
jehorton@usaid.gov
Dan.Parry@ssa.gov
Stephen.moore@treasury.gov

## Slide 38: OGCs Contact Information
Alfred M. Pollard (FHFA) <Alfred.Pollard@fhfa.gov>; Angela Freyre (Ex-Im) <angela.freyre@exim.gov>; Anne Small (SEC) <SmallA@sec.gov>; Arthur Gary (DOJ) <Arthur.Gary@usdoj.gov>; Avi Garbow (EPA) <garbow.avi@epa.gov>; Bosworth, Michael; Brady, Hugh; Christopher Meade (Treasury) <Christopher.Meade@treasury.gov>; Damon Smith (HUD) <damon.y.smith@hud.gov>; David Black (SSA) <David.Black@ssa.gov>; Dawn Starr (FMCS) <DStarr@fmcs.gov>; Douglas Kramer (USAID) <dkramer@usaid.gov>; Gary Stern (NARA) <Garym.stern@nara.gov>; Hilary Tompkins (DOI) <Hilary.Tompkins@sol.doi.gov>; James Cole, Jr. (Ed) <james.cole@ed.gov>; Jeffrey Prieto (USDA) <Jeffrey.prieto@ogc.usda.gov>; Jonathan E. Nuechterlein (FTC) <jnuechterlein@ftc.gov>; Jonathan Marcus (CFTC) <jmarcus@cftc.gov>; Jonathan Sallet (FCC) <Jonathan.sallet@fcc.gov>; Kamala Vasagam (OPM) <Kamala.Vasagam@opm.gov>; Kathryn B. Thomson (DOT) <Kathryn.thomson@dot.gov>; Kelly Welsh (DOC) <kwelsh@doc.gov>; Kimberly Heimert (OPIC) <Kimberly.Heimert@opic.gov>; Kris Durmer (GSA) <Kris.durmer@gsa.gov>; Lawrence Rudolph (NSF) <lrudolph@nsf.gov>; Leigh A. Bradley (VA) <leigh.bradley@va.gov>; Leonard, Rachael; Lisa Stevenson (FEC) <lstevenson@fec.gov>; M. Patricia Smith (DOL) <smith.m.patricia@dol.gov>; Maame Ewusi-Mensah Frimpong (MCC) <frimpongme@mcc.gov>; Mallory, Brenda; Margaret Doane (NRC) <margaret.doane@nrc.gov>; Martz, Stephanie; Mary McLeod (State) <mcleodM@state.gov>; Melvin Williams (SBA) <Melvin.Williams@sba.gov>; Meredith Fuchs (CFPB) <Meredith.Fuchs@cfpb.gov>; Michael McKenna (NCUA) <mmckenna@ncua.gov>; Nancy Weiss (IMLS) <Nweiss@imls.gov>; O'Connor, Jennifer; Paul Kollmer-Dorsey (BBG) <PKollmer@bbg.gov>; Reif, Timothy M.; Richard F. Griffin, Jr. (NLRB) <Richard.griffin@nlrb.gov>; Richard J. Osterman, Jr. (FDIC) <rosterman@fdic.gov>; Richard Reback (DNFSB) <richardr@dnfsb.gov>; Robert S. Litt (ODNI) <Robert.Litt@dni.gov>; Rudy Mehrbani (Peace Corps) <rmehrbani@peacecorps.gov>; Scott G. Alvarez (Fed) <Scott.alvarez@frb.gov>; Stephanie Tsacoumis (CPSC) <stsacoumis@cpsc.gov>; Robert Taylor (DOD) <Robert.s.taylor134.civ@mail.mil>; Stevan Bunnell (DHS) <stevan.bunnell@hq.dhs.gov>; Steven Croley (DOE) <steven.croley@hq.doe.gov>; Sumara M. Tompson-King (NASA) <sumara.m.thompson-king@nasa.gov>; Teitz, Jeff; Valerie Green (CNCS) <VGreen@cns.gov>; William Schultz (HHS) <william.schultz@hhs.gov>

## Slide 39: FITARA/FISMA Executive Working Group (FFEWG) Nominations
Ellen Murray – ASFR/CAO, HHS; Ellen.Murrayhhs.gov
Richard McKinney – CIO, DOT; richard.mckinney@dot.gov
E.J. (Ned) Holland – ASA/HHS; Ned.Holland@hhs.gov
Frank Baitman – CIO, HHS; Frank.Baitman@hhs.gov
Joe Klimavicz – CIO, DOJ; jklimavicz@jmd.usdoj.gov
Sanjeev (Sonny) Bhagowalia – CIO, Treasury
Cheryl Cook – CIO, USDA; Cheryl.Cook@ocio.usda.gov
Jon Holladay – CFO, USDA; Jon.Holladay@cfo.usda.gov
Mary Pletcher – CHCO from the Department of the Interior; Mary_Pletcher@ios.doi.gov
Kevin Mahoney – CHCO, Commerce; kmahoney@doc.gov
Cynthia Vaughan – Deputy CHCO, DOT; cynthia.vaughan@dot.gov
Terry Halvorsen – DOD CIO; terry.a.halvorsen2.civ@mail.mil
David M. Klaus – Deputy Under Secretary for Management and Performance, DOE; David.Klaus@Hq.Doe.Gov
Stan Meiburg – Acting Deputy Administrator, EPA; Meiburg.Stan@epa.gov
Rick Chandler – Director, Policy & Planning, Office of CIO, DOJ; Richard.Chandler@usdoj.gov
Krista Paquin – Deputy Associate Administrator for Mission Support, NASA; krista.c.paquin@nasa.gov
T. Michael Kerr – Assistant Secretary for Administration and Management, DOL; Kerr.Michael@dol.gov
Angela Bailey – Chief Operating Officer, OPM; Angela.Bailey@opm.gov
Bill Zielinski – CIO/Deputy Commissioner for Systems, SSA; Bill.Zielinski@ssa.gov
Angelique Crumbly – Head of Management Bureau with CIO Oversight, USAID; acrumbly@usaid.gov
Stephen Warren – VA CIO; Stephen.Warren@va.gov
Ellen Herbst – CFO/ASA; EHerbst@doc.gov

## Slide 40: FFEWG Nominations
Name and title | Agency | Email | Community
Ellen Murray – ASFR/CAO | HHS | Ellen.Murrayhhs.gov | CAO
Richard McKinney – CIO | DOT | richard.mckinney@dot.gov | CIO
E.J. (Ned) Holland – ASA | HHS | Ned.Holland@hhs.gov | ASAM
Frank Baitman – CIO | HHS | Frank.Baitman@hhs.gov | CIO
Joe Klimavicz – CIO | DOJ | jklimavicz@jmd.usdoj.gov | CIO
Sanjeev (Sonny) Bhagowalia – CIO | Treasury | sonny.bhagowalia@treasury.gov | CIO
Cheryl Cook – CIO | USDA | Cheryl.Cook@ocio.usda.gov | CIO
Jon Holladay – CFO | USDA | Jon.Holladay@cfo.usda.gov | CFO
Mary Pletcher – CHCO | Interior | Mary_Pletcher@ios.doi.gov | CHCO
Kevin Mahoney – CHCO | Commerce | kmahoney@doc.gov | CHCO
Cynthia Vaughan – Deputy CHCO | DOT | cynthia.vaughan@dot.gov | CHCO
Name and title | Agency | Email | Community
Terry Halvorsen – CIO | DOD | terry.a.halvorsen2.civ@mail.mil | CIO
David M. Klaus – Deputy Under Secretary for Management and Performance | DOE | David.Klaus@Hq.Doe.Gov | ASAM
Stan Meiburg – Acting Deputy Administrator | EPA | Meiburg.Stan@epa.gov | ASAM
Rick Chandler – Director, Policy & Planning, Office of CIO | DOJ | Richard.Chandler@usdoj.gov | CIO
Krista Paquin – Deputy Associate Administrator for Mission Support | NASA | krista.c.paquin@nasa.gov | ASAM
T. Michael Kerr – Assistant Secretary for Administration and Management | DOL | Kerr.Michael@dol.gov | ASAM
Angela Bailey – Chief Operating Officer | OPM | Angela.Bailey@opm.gov | ASAM
Bill Zielinski – CIO/Deputy Commissioner for Systems | SSA | Bill.Zielinski@ssa.gov | CIO
Angelique Crumbly – Head of Management Bureau with CIO Oversight | USAID | acrumbly@usaid.gov | ASAM
Stephen Warren – CIO | VA | Stephen.Warren@va.gov | CIO
Ellen Herbst – CFO/ASA | Commerce | EHerbst@doc.gov | CFO